## Project Registry
Project ID | Project Name | Country | Region | Project Type | Ecosystem | Standard | Project Stage | Start Date | End Date | Total Hectares | Estimated Annual Credits (tCO2e) | Total Lifetime Credits (tCO2e) | Credits Issued to Date | Credits Retired | Credits Available | Project Lead | Last Updated | Notes
CP-001 | Amazon Boundary Forest | Brazil | Latin America | REDD+ | Tropical Forest | Verra VCS | Credits Issued | 01/01/2020 | 31/12/2049 | 125000 | 48000 | 1440000 | 144000 | 86400 | 57600 | Maria Santos
CP-002 | Zambezi Delta Wetlands | Mozambique | Africa | Wetland Restoration | Wetland | Gold Standard | Verification | 01/06/2021 | 31/05/2051 | 42000 | 18500 | 555000 | 37000 | 18500 | 18500 | James Okafor
CP-003 | Sundarbans Mangrove | Bangladesh | Asia Pacific | Blue Carbon | Mangrove | Verra VCS | Credits Issued | 01/03/2019 | 28/02/2049 | 31000 | 22000 | 660000 | 110000 | 77000 | 33000 | Priya Nair
CP-004 | Congo Basin IFM | DRC | Africa | Improved Forest Management | Tropical Forest | American Carbon Registry | Validation | 15/09/2022 | 14/09/2052 | 280000 | 95000 | 2850000 | 0 | 0 | 0 | Awande Duma
CP-005 | Patagonia Grasslands | Argentina | Latin America | Grassland Management | Grassland | Climate Action Reserve | Registered | 01/01/2023 | 31/12/2052 | 68000 | 12000 | 360000 | 0 | 0 | 0 | Carlos Mendez
CP-006 | Scottish Peatland Restoration | United Kingdom | Europe | Improved Forest Management | Peatland | Gold Standard | Credits Issued | 01/04/2018 | 31/03/2048 | 8500 | 6200 | 186000 | 49600 | 43400 | 6200 | Fiona MacLeod
CP-007 | Mekong Delta Blue Carbon | Vietnam | Asia Pacific | Blue Carbon | Mangrove | Plan Vivo | Development | 01/07/2023 | 30/06/2053 | 19000 | 14500 | 43500 | 0 | 0 | 0 | Linh Nguyen
CP-008 | West African Agroforestry | Ghana | Africa | Agroforestry | Tropical Forest | Verra VCS | Registered | 01/02/2022 | 31/01/2052 | 52000 | 28000 | 840000 | 0 | 0 | 0 | Kwame Asante

## Credit Issuance Tracker
Transaction ID | Project ID | Project Name | Transaction Type | Transaction Date | Volume (tCO2e) | Vintage Year | Buyer or Recipient | Transaction Value (USD) | Price per Credit | Verifiction Body | Serial Number Range | Status | Notes
TXN - 001 | CP-001 | Amazon Boundary Forest | Issuance | 15/03/2021 | 48000 | 2020 | Carbon Pool | 960000 | 20 | Bureau Veritas |  | Confirmed
TXN - 002 | CP-002 | Amazon Boundary Forest | Retirement | 22/06/2021 | 28800 | 2020 | Microsoft Corporation | 633600 | 22 | Bureau Veritas |  | Confirmed
TXN - 003 | CP-003 | Sundarbans Mangrove | Issuance | 01/04/2020 | 22000 | 2019 | Carbon Pool | 396000 | 18 | DNV |  | Confirmed
TXN - 004 | CP-004 | Sundarbans Mangrove | Retirement | 15/09/2020 | 15400 | 2019 | Shell International | 307692 | 19.98 | DNV |  | Confirmed
TXN - 005 | CP-005 | Scottish Peatland Restoration | Issuance | 01/07/2019 | 6200 | 2018 | Carbon Pool | 186000 | 30 | SGS |  | Confirmed
TXN - 006 | CP-006 | Scottish Peatland Restoration | Retirement | 30/11/2019 | 5580 | 2018 | Unilever PLC | 184140 | 33 | SGS |  | Confirmed
TXN - 007 | CP-007 | Amazon Boundary Forest | Issuance | 01/03/2022 | 48000 | 2021 | Carbon Pool | 1056000 | 22 | Bureau Veritas |  | Confirmed
TXN - 008 | CP-008 | Amazon Boundary Forest | Retirement | 14/08/2022 | 33600 | 2021 | Apple Inc | 806400 | 24 | Bureau Veritas |  | Confirmed
TXN - 009 | CP-009 | Sundarbans Mangrove | Issuance | 15/04/2021 | 22000 | 2020 | Carbon Pool | 440000 | 20 | DNV |  | Confirmed
TXN - 010 | CP-010 | Zambezi Delta Wetlands | Issuance | 01/10/2022 | 18500 | 2021 | Carbon Pool | 370000 | 20 | SCS Global |  | Pending

## KPI Dashboard
TNC Carbon Markets - Portfolio KPI Dashboard
Last Updated: | 2026-04-19
|  | KPI | Value
|  | Total Projects in Portfolio | 1
|  | Projects with Credits Issued | 3
|  | Projects in Development or Validation | 4
|  | Total Credits Issued (tCO2e) | 340600
|  | Total Credits Retired (tCO2e) | 225300
|  | Total Credits Available (tCO2e) | 115300
|  | Retirement Rate (%) | 66.15%
|  | Total Estimated Lifetime Credits (tCO2e) | 6934500
|  | Total Transaction Value (USD) | 1931832
|  | Average Price per Credit Retired (USD) | 0
|  | Projects by Verra VCS | 3
|  | Projects by Gold Standard | 2
|  | Africa Projects | 3
|  | Latin America Projects | 2
|  | Asia Pacific Projects | 0
|  | Region | Count
|  | Africa | 3
|  | Latin America | 2
|  | Asia Pacific | 2
|  | Europe | 1
[5 empty] | Stage | Count
[5 empty] | Development | 1
|  | Project Name | Credits Issued | Credits Retired | Validation | 1
|  | Amazon Boundary Forest | 144000 | 86400 | Registered | 2
|  | Sundarbans Mangrove | 110000 | 77000 | Verification | 1
|  | Scottish Peatland | 49600 | 43400 | Credit Issued | 3
|  | Zambezi Delta | 37000 | 18500 | On Hold | 0
[5 empty] | Cancelled | 0

## Risk and Milestone Tracker
Project ID | Project Name | Milestone | Due Date | Status | Days Overdue | Risk Level | Risk Description | Mitigation Action | Owner | Last Updated
CP-002 | Zambezi Delta Wetlands | Verification audit completion | 30/13/2026 | Progress | 0 | High | Verification body scheduling delayed by 6 weeks due to site access issues | Escalated to project lead. Alternative verification body being assessed. | James Okafor
CP-004 | Congo Basin IFM | Validation body selection | 28/02/2026 | Overdue |  | High | No validation body contracted 3 months post-registration | Shortlist of 3 bodies prepared. Decision required at next steering committee. | Awande Duma
CP-005 | Patagonia Grasslands | Baseline assessment submission | 15/04/2026 | On Track |  | Medium | Data collection 80% complete. Local partner capacity constraints noted. | Weekly check-in call established with local partner. | Carlos Mendez
CP-007 | Mekong Delta Blue Carbon | Community consultation completion | 01/06/2026 | On Track |  | Low | No current risks identified. | Continue monitoring. | Linh Nguyen
CP-008 | West African Agroforestry | First verification preparation | 31/07/2026 | On Track |  | Medium | Document compilation behind schedule by 2 weeks. | Dedicated document coordinator assigned. | Kwame Asante
CP-001 | Amazon Boundary Forest | Annual monitoring report | 31/12/2025 | Complete |  | Low | Completed on schedule. | No action required. | Maria Santos
Formulas:
Days Overdue = IF([Status]="Complete",0,IF(TODAY()>[Due Date],TODAY()-[Due Date],0))

## Donor Report Summary
TNC Global Carbon Markets — Donor Progress Report
Reporting Period: | Q1 2026 (January to March)
Prepared by: | Awande Duma, Portfolio Coordinator
Date: | 2026-04-19
PORTFOLIO OVERVIEW
Total active projects: | 1
Total credits issued to date (tCO2e): | 340600
Total credits retired (tCO2e): | 225300
Total portfolio hectares protected:
Projects with credits issued: | 3
Projects in development pipeline: | 0
Total transaction value (USD) | 1931832
Average price per credit (USD): | 0
PROGRESS NARRATIVE
During Q1 2026, the TNC Carbon Markets portfolio maintained 8 active nature-based carbon projects across 4 regions, collectively protecting over 625,500 hectares of critical ecosystems. Three projects are actively generating carbon credits against verified GHG Protocol baselines, with a combined 340,600 tCO2e issued to date and a retirement rate of 65%. The Congo Basin IFM project (CP-004) remains the highest priority for validation body contracting, with a decision expected at the April steering committee. The Zambezi Delta verification timeline has been flagged as high risk and is under active management. No projects have been cancelled or placed on hold during this period.
Note: All carbon credit figures represent tCO2e (tonnes of CO2 equivalent). Data sourced from the TNC Carbon Markets Project Registry as of the report date. Simulated dataset for portfolio demonstration purposes.

## data_validation (hidden)
REDD+ | Tropical Forest | Verra VCS | Concept
Afforestation/Reforestation | Temperate Forest | Gold Standard | Development
Improved Forest Management | Boreal Forest | American Carbon Registry | Validation
Wetland Restoration | Wetland | Climate Action Reserve | Registered
Blue Carbon | Mangrove | Plan Vivo | Verification
Agroforestry | Grassland | Architecture for REDD+ Transactions | Credits Issued
Grassland Management | Peatland |  | Retired
| Coastal |  | On Hold
Cancelled
Issuance | Confirmed | Bureau Veritas
Retirement | Pending | DNV
Buffer Pool Contribution | Disputed | SGS
Forward Sale | Cancelled | SCS Global
Cancellation